## README
Lorraine Travel - SEO / AEO / GEO Project Tracker
Purpose | Single source of truth for every SEO, AEO and GEO issue and opportunity: identified, prioritized, implemented, tracked, measured.
Website | https://www.lorrainetravel.com
Created | 2026-10-05 (from the 2026-10-05 audit and the SEO / AEO / GEO proposal)
Blue text | Cells you edit (inputs). Black text = formulas; do not overwrite.
Workflow | 1) Log every issue as a row in Master Tracker. 2) Set Priority, Impact, Effort; work High impact + Low/Medium effort first. 3) Move Status as work progresses. 4) On Completed, set Date completed, fill After metrics, copy the row to Completed Work, set a Follow-up date 30 days out. 5) Review the KPI Dashboard monthly.
Statuses | Identified, Planned, In Progress, Waiting for Client, Waiting for Developer, Testing, Monitoring, Completed
Priority | Critical = blocks indexing or causes penalties (fix now). High = significant ranking impact (within 1 week). Medium = optimization (within 1 month). Low = backlog.
Tabs | Master Tracker (all tasks; pre-filled with the 18 tasks of the 30-day plan) ¦ Technical SEO ¦ Content SEO ¦ Keywords & Rankings ¦ Google Search Console ¦ AEO-GEO Opportunities ¦ Schema ¦ Backlinks ¦ Local SEO ¦ Competitor Tracking ¦ Completed Work ¦ KPI Dashboard
Example rows | Rows already filled in Master Tracker are the real 30-day plan tasks (all Status = Planned/Identified, no dates started). Other tabs hold a few starting rows drawn from the audit; replace or extend them.
Assumptions | Baselines are blank: Search Console, GA4, Semrush and Google Business Profile data had not been provided when this was built. Target growth percentages on the KPI Dashboard are the low end of the proposal ranges and are directional, not guarantees.
Source | Audit findings: lorrainetravel.com-audit/FULL-AUDIT-REPORT.md (2026-10-05). Plan: SEO, AEO & GEO Optimization Proposal.

## KPI Dashboard
KPI Dashboard
Blue = enter monthly. Targets are directional low-end growth from the proposal, not guarantees.
Task status | Count |  | Priority (open tasks) | Count |  | Category (all tasks) | Count
Identified |  |  | Critical |  |  | Technical
Planned |  |  | High |  |  | On-page
In Progress |  |  | Medium |  |  | Content
Waiting for Client |  |  | Low |  |  | Schema
Waiting for Developer | [5 empty] | Performance
Testing | [5 empty] | Local
Monitoring | [5 empty] | AEO
Completed | [5 empty] | GEO
Total tasks | [5 empty] | Measurement
% completed | [5 empty] | Reporting
Overdue
KPI | Direction | Baseline | Current | Change vs baseline | 90-day target change | 6-month target change | Status vs 90-day
Organic impressions | Higher |  |  |  | 10% | 30%
Organic clicks | Higher |  |  |  | 10% | 25%
CTR | Higher |  |  |  | 10% | 20%
Average position (improvement) | Lower |  |  |  | 10% | 20%
Ranking keywords | Higher |  |  |  | 15% | 40%
Top 10 rankings | Higher |  |  |  | 20% | 50%
Indexed pages | Higher |  |  |  | 10% | 40%
Organic sessions (GA4) | Higher |  |  |  | 10% | 25%
Organic leads / conversions | Higher |  |  |  | 10% | 20%
Organic conversion rate | Higher |  |  |  | 5% | 15%
GBP views | Higher |  |  |  | 10% | 25%
Referring domains | Higher |  |  |  | 10% | 30%
Featured snippets | Higher |  |  |  | 20% | 50%
AI citations (of 25-question test) | Higher |  |  |  | 20% | 40%
Core Web Vitals pass rate (% URLs) | Higher |  |  |  | 10% | 25%
Notes: enter Baseline and Current from Search Console, GA4, Semrush and Google Business Profile. For average position enter the position number; a lower number is better, so a negative Change vs baseline counts as improvement. Formulas calculate when the file is opened in Excel or Google Sheets.

## Master Tracker
ID | Date identified | Website / project | Page URL | Category | Issue / opportunity | Description | Priority | Impact | Effort | Recommended action | Assigned to | Date started | Target completion | Status | Date completed | Before metrics | After metrics | KPI affected | Google Search Console status | Indexing status | Ranking / keyword | Notes | Follow-up date | Overdue?
T-001 | 2026-10-05 | lorrainetravel.com | Site-wide | Measurement | No performance baseline (Search Console, GA4, Bing, Semrush not connected) | No clicks, impressions, position, traffic or conversion baseline exists | High | High | Low | Get Search Console, GA4, Bing Webmaster, Semrush access; export 16 months of data; record 50-100 keyword baseline | SEO + Client |  | 2026-10-09 | Waiting for Client |  |  |  | All KPIs | Not checked | Not checked |  |  | 2026-10-09
T-002 | 2026-10-05 | lorrainetravel.com | https://lorrainetravel.com/ | Technical | Apex HTTPS fails TLS handshake | Audit sandbox got 'sslv3 alert handshake failure' on bare domain; www works. Verify before changing. | High | High | Low | Test from 3 networks; if confirmed fix Cloudflare certificate for apex and 301 to https://www | Developer |  | 2026-10-13 | Identified |  |  |  | Organic clicks, indexed pages | Not checked | Not checked |  |  | 2026-10-13
T-003 | 2026-10-05 | lorrainetravel.com | /destinations/* (9 pages) | On-page | 9 destination pages share one meta description | 'Editorial travel guide written by Lorraine Travel advisors.' (59 chars) also used as og:description | High | High | Low | Write unique 120-155 char descriptions with destination, hook and CTA; align og:description | SEO |  | 2026-10-16 | Identified |  |  |  | CTR, impressions | Not checked | Not checked |  |  | 2026-10-16
T-004 | 2026-10-05 | lorrainetravel.com | 15 pages incl. homepage | On-page | Titles over 60 characters | Homepage 75 chars; Orient Express post 89 | Medium | Medium | Low | Rewrite to 50-60 chars, primary keyword first, brand last | SEO |  | 2026-10-16 | Identified |  |  |  | CTR | Not checked | Not checked |  |  | 2026-10-16
T-005 | 2026-10-05 | lorrainetravel.com | 14 pages | On-page | Meta descriptions over 160 characters | Up to 245 chars (/cruises) | Medium | Medium | Low | Trim to 140-155 chars with one benefit and one CTA | SEO |  | 2026-10-20 | Identified |  |  |  | CTR | Not checked | Not checked |  |  | 2026-10-20
T-006 | 2026-10-05 | lorrainetravel.com | Top 10 pages | Performance | Core Web Vitals not measured | No LCP, INP, CLS data | High | High | Low | Run PageSpeed Insights and CrUX, mobile and desktop; log values and fix list | SEO |  | 2026-10-16 | Planned |  |  |  | CWV pass rate | Not checked | Not checked |  |  | 2026-10-16
T-007 | 2026-10-05 | lorrainetravel.com | Top 10 pages | Technical | Mobile usability unverified | No mobile screenshots or Search Console mobile report reviewed | High | High | Low | Capture mobile screenshots; test menu, tap targets, forms | SEO |  | 2026-10-20 | Planned |  |  |  | Mobile CWV, conversions | Not checked | Not checked |  |  | 2026-10-20
T-008 | 2026-10-05 | lorrainetravel.com | https://www.lorrainetravel.com/ | Technical | No security headers | No HSTS, CSP, X-Frame-Options, X-Content-Type-Options in homepage response | Medium | Medium | Medium | Add HSTS, X-Content-Type-Options, Referrer-Policy, frame-ancestors, Permissions-Policy via Cloudflare or app | Developer |  | 2026-10-30 | Identified |  |  |  | Technical health score | Not checked | Not checked |  |  | 2026-10-30
T-009 | 2026-10-05 | lorrainetravel.com | https://www.lorrainetravel.com/sitemap.xml | Technical | Sitemap lastmod identical on all URLs | Every URL has lastmod 2026-10-05 (build date) | Medium | Medium | Low | Set lastmod to real modification dates; resubmit in Search Console and Bing | Developer |  | 2026-10-23 | Identified |  |  |  | Indexed pages, crawl stats | Not checked | Not checked |  |  | 2026-10-23
T-010 | 2026-10-05 | lorrainetravel.com | All 36 sitemap URLs | Technical | Indexing status of 36 URLs unknown | Not verified in Search Console | High | High | Low | URL Inspection; fix 'crawled/discovered - not indexed' | SEO |  | 2026-10-23 | Planned |  |  |  | Indexed pages | Not checked | Not checked |  |  | 2026-10-23
T-011 | 2026-10-05 | lorrainetravel.com | Site-wide | Technical | Full crawl for broken links and redirect chains not done | Audit covered 36 sitemap URLs only | High | Medium | Low | Crawl all internal links, images, outbound; fix 4xx/5xx and chains | SEO + Developer |  | 2026-10-23 | Planned |  |  |  | Crawl errors | Not checked | Not checked |  |  | 2026-10-23
T-012 | 2026-10-05 | lorrainetravel.com | Site-wide | Technical | Canonical / duplicate risk unverified for parameters and trailing slashes | Canonicals self-reference on 36 pages; parameter URLs not tested | Medium | Medium | Low | Verify single canonical host and path pattern | SEO |  | 2026-10-23 | Planned |  |  |  | Indexed pages | Not checked | Not checked |  |  | 2026-10-23
T-013 | 2026-10-05 | lorrainetravel.com | All schema templates | Schema | Schema validated by pattern only | JSON-LD detected; not run through validators | Medium | Medium | Low | Validate in Rich Results Test and Schema Validator; add Article author/dates; BreadcrumbList on all guides | SEO |  | 2026-10-27 | Planned |  |  |  | Valid structured data | Not checked | Not checked |  |  | 2026-10-27
T-014 | 2026-10-05 | lorrainetravel.com | Homepage + other pages | Content | Missing alt text on images | 2 homepage images; 1-2 on most pages | Low | Low | Low | Add descriptive alt text | SEO + Client |  | 2026-10-27 | Identified |  |  |  | Image impressions | Not checked | Not checked |  |  | 2026-10-27
T-015 | 2026-10-05 | lorrainetravel.com | Priority questions | GEO | No AI-visibility baseline | Citation in AI Overviews, ChatGPT, Perplexity, Copilot unmeasured | High | High | Low | Test 25 priority questions; log citations and mentions | SEO |  | 2026-10-20 | Planned |  |  |  | AI citations, brand mentions | Not checked | Not checked |  |  | 2026-10-20
T-016 | 2026-10-05 | lorrainetravel.com | Top 5 destination/service pages | AEO | FAQPage schema on homepage only | Question queries unclaimed | Medium | High | Medium | Add 5-8 Q&A blocks with FAQPage markup | SEO + Client |  | 2026-10-30 | Planned |  |  |  | Snippets, AI citations | Not checked | Not checked |  |  | 2026-10-30
T-017 | 2026-10-05 | lorrainetravel.com | Google Business Profile | Local | GBP unverified | Categories, NAP, hours, services, reviews not audited | High | High | Low | Audit and correct GBP | SEO + Client |  | 2026-10-27 | Waiting for Client |  |  |  | GBP views, calls | Not checked | Not checked |  |  | 2026-10-27
T-018 | 2026-10-05 | lorrainetravel.com | This workbook | Reporting | Tracker and weekly reporting not live |  | High | High | Low | Import findings; send first weekly update | SEO |  | 2026-10-12 | In Progress |  |  |  | Reporting cadence | Not checked | Not checked |  |  | 2026-10-12
Formulas:
Overdue? = IF(AND([Target completion]<>"",[Status]<>"Completed",[Target completion]<TODAY()),"Overdue","")

## Technical SEO
ID | Date identified | Page / template | Issue | Check / tool | Priority | Assigned to | Status | Date fixed | Before | After | Verified (Y/N) | Notes
TS-001 | 2026-10-05 | https://lorrainetravel.com/ | Apex HTTPS TLS handshake failure (verify) | curl / SSL Labs | High | Developer | Identified |  |  |  |  | Sandbox result; re-test from 3 networks
TS-002 | 2026-10-05 | https://www.lorrainetravel.com/ | No security headers | securityheaders.com | Medium | Developer | Identified
TS-003 | 2026-10-05 | /sitemap.xml | lastmod identical on all URLs | Search Console Sitemaps | Medium | Developer | Identified

## Content SEO
ID | Date identified | Page URL | Opportunity | Current words | Target words | Primary keyword | Priority | Assigned to | Status | Date published | Before (clicks/pos.) | After (clicks/pos.) | Notes
CS-001 | 2026-10-05 | /destinations/japan-luxury | Expand guide: itinerary, seasons, properties, FAQ, advisor author | 382 | 1200 | luxury japan travel | High | SEO + Client | Identified |  |  |  | Same pattern for the other 8 /destinations/* guides
CS-002 | 2026-10-05 | /resources/climate | Thin page; expand with month-by-month table | 251 | 600 |  | Medium | SEO | Identified
CS-003 | 2026-10-05 | /blog | Only 4 posts; plan 4-6 new articles from gap analysis |  |  |  | Medium | SEO + Client | Identified

## Keywords & Rankings
Keyword | Target URL | Intent | Monthly volume | Baseline position | Baseline date | Week 1 | Week 2 | Week 3 | Week 4 | Current position | Change vs baseline | SERP feature | Notes
lorraine travel | https://www.lorrainetravel.com/ | Brand | [10 empty] | Brand baseline; fill from Search Console / Semrush

## Google Search Console
Week starting | Clicks | Impressions | CTR | Avg position | Pages indexed | Pages not indexed | Sitemap status | Coverage / indexing issues | Mobile usability issues | Rich-result errors | Notes

## AEO-GEO Opportunities
ID | Date identified | Type (AEO/GEO) | Question / topic | Target page | Platform tested | Cited? (Y/N) | Competitor cited | Action | Priority | Assigned to | Status | Date retested | Notes
AG-001 | 2026-10-05 | AEO | Best time to visit [destination] (one per guide) | /destinations/* |  |  |  | Add 40-60 word direct answer + table + FAQ markup | High | SEO | Identified
AG-002 | 2026-10-05 | GEO | Who are the oldest luxury travel agencies in America? (brand/entity) | /about |  |  |  | Facts page: founders, 1948 Havana, 1960 Coral Gables, affiliations; keep llms.txt current | High | SEO + Client | Identified

## Schema
Template / page type | Example URL | Schema types present | Validated (Y/N) | Errors | Warnings | Rich-result eligible | Fix needed | Assigned to | Status | Date validated | Notes
Homepage | https://www.lorrainetravel.com/ | Organization, TravelAgency, Place, GeoCoordinates, OpeningHours, WebSite+SearchAction, WebPage, Offer, FAQPage | N |  |  |  | Validate; check Offer fields | SEO | Planned |  | Detected in audit 2026-10-05
Destination guide | https://www.lorrainetravel.com/destinations/japan-luxury | Article, BreadcrumbList, Organization, WebSite, Person | N |  |  |  | Validate; add author and dates; add FAQPage | SEO | Planned

## Backlinks
Date found | Target / source domain | URL | Type | Link status | Anchor text | Authority (DR/DA) | Priority | Assigned to | Outreach status | Date contacted | Date won | Notes
2026-10-05 | Four Seasons (Preferred Partner page) |  | Partner listing | Prospect |  |  | High | Client | Identified |  |  | Confirm partner page links to lorrainetravel.com
2026-10-05 | Signature Travel Network |  | Member directory | Prospect |  |  | High | Client | Identified
2026-10-05 | ASTA |  | Member directory | Prospect |  |  | Medium | Client | Identified

## Local SEO
ID | Date identified | Item | Platform | Current value | Correct value (NAP) | Priority | Assigned to | Status | Date fixed | Notes
LS-001 | 2026-10-05 | Google Business Profile audit | Google |  | 377 Alhambra Circle, Coral Gables, FL 33134; +1 305 446 4433 | High | SEO + Client | Waiting for Client |  | NAP from llms.txt; confirm with client
LS-002 | 2026-10-05 | Review-request process | Google / Tripadvisor |  |  | Medium | Client | Identified
LS-003 | 2026-10-05 | Citation clean-up (20-30 directories) | Directories |  |  | Medium | SEO | Identified

## Competitor Tracking
Competitor | Domain | Date checked | Est. organic keywords | Est. organic traffic | Referring domains | Top pages / content gaps | AI citations (platform) | Notes / action
(add 3-5 competitors from client) | [7 empty] | Needs client-provided competitor list and Semrush API units

## Completed Work
ID | Date completed | Category | Page URL | What was done | KPI affected | Before | After | Measured on (follow-up) | Result / notes